## Sprint 2
ID | Work Item Type | Title | Assigned To | State | Original Estimate | Remaining Work | Testing date | Release date
116 | Task | QC TASK: User is able to log into the system, so that user can access the system according to user’s authority (4) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Active | 4 | 2
117 | Task | QC TASK: User is able to log out (30) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Active | 2 | 1 | 2021-08-11 | 2021-08-12
109 | Task | QC TASK: User is able to change the password (28) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Active | 3 | 2 | 2021-08-13 | 2021-08-14
114 | Task | QC TASK: Admin is able to disable user (7) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Active | 4 | 3 | 2021-08-12 | 2021-08-13
115 | Task | QC TASK: Admin is able to edit user information (6) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Active | 12 | 9 | 2021-08-13 | 2021-08-14
113 | Task | QC TASK: Admin is able to edit asset information (10) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Active | 10 | 7 | 2021-08-12 | 2021-08-13