## Sprint 2
ID | Work Item Type | Title | Assigned To | State | Original Estimate | Completed date | Dev
116 | Task | QC TASK: User is able to log into the system, so that user can access the system according to user’s authority (4) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 4 | 2021-08-21 | Hong Dai Duong
109 | Task | QC TASK: User is able to change the password (28) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 3 | 2021-08-21 | Nguyen Do Duc Hao
378 | Task | QC TASK: Admin is able to delete assignment (15) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 8 | 2021-08-22 | Nguyen Do Duc Hao
393 | Task | QC TASK: Admin is able to delete asset (11) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 8 | 2021-08-22 | Hoàng Nhii
376 | Task | QC TASK: Admin is able to edit assignment (14) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 10 | 2021-08-23 | Cường Nguyễn Chí
113 | Task | QC TASK: Admin is able to edit asset information (10) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Active | 10 |  | Nguyen Do Duc Hao