## Sprint 2
ID | Work Item Type | Title | Assigned To | State | Original Estimate | Completed date | Dev
508 | Task | QC TASK: Admin is able to view request for returning (17) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 8 | 2021-08-28 | Cường Nguyễn Chí
517 | Task | QC TASK: Admin is able to complete returning request (23) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 6 | 2021-08-28 | Hong Dai Duong
520 | Task | QC TASK: Admin is able to cancel request for retuning (24) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 7 | 2021-08-27 | Nguyen Do Duc Hao
523 | Task | QC TASK: Admin is able to export report (26) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 2 | 2021-08-26 | Hưng Nguyễn
113 | Task | QC TASK: Admin is able to edit asset information (10) | Dinh Le Song Binh <binhdlt1999@gmail.com> | Closed | 10 | 2021-08-25 | Nguyen Do Duc Hao