## Sprint 2
ID | Work Item Type | Title | Assigned To | State | Original Estimate | Testing date | Release date
508 | Task | QC TASK: Admin is able to view request for returning (17) | Dinh Le Song Binh <binhdlt1999@gmail.com> | New | 8 | 2021-08-26 | 2021-08-27
517 | Task | QC TASK: Admin is able to complete returning request (23) | Dinh Le Song Binh <binhdlt1999@gmail.com> | New | 6 | 2021-08-27 | 2021-08-28
520 | Task | QC TASK: Admin is able to cancel request for retuning (24) | Dinh Le Song Binh <binhdlt1999@gmail.com> | New | 7 | 2021-08-28 | 2021-08-29
523 | Task | QC TASK: Admin is able to export report (26) | Dinh Le Song Binh <binhdlt1999@gmail.com> | New | 2 | 2021-08-25 | 2021-08-26